## Sheet1
Date | Action | Feature | Backlog | Priority | Completed
2017-02-07 | Refactored carService to return promise (via SO question) | Wishlist | Add Wishlist to Identity Table for AspNetUser
2017-02-07 | Render pagination links via ng-repeat | WishList | Ad to Wishlist - adds record to Db
2017-02-07 | Set active class of current page when clicked on pagination links. | Wishlist | Add Heart & Heart-o - When users adds it chage fa icon
2017-02-08 | Moved Categories partial view to angular directive | Wishlist | Hook up link to show Wishlist and display
2017-02-08 | Investigate Pagination bug & fix | Wishlist | Remove from WishList - remove from Db
2017-02-08 | Make start on Details page - pass in Id value
2017-02-08 | Answer 2 x Stack Overflow Questions | Login | User can log in from modal
2017-02-08 | Read chapter of Web API 2 book | Login | Appstrap Login and Register Pages
2017-02-09 | Get all Car Info Data (Console app - wikiApi)
2017-02-09 | Added car spec table directive to car details page | Homepage | Update Homepage with new info, video etc.
2017-02-09 | Read chapter of Design Patterns Book | Homepage | Add Google chart to Homepage
2017-02-10 | Added Car Info to DB - added car info service and output to details page
2017-02-10 | Add images from API call to carousel on Details page | Recommended | Show Recommended & similar cars on Bottom Detail Page
2017-02-11 | Added search algorithm
2017-02-11 | Investigate Partial view, directive issue - Header | Reviews | Reviews - and Ratings - Stars fa icons
2017-02-12 | Hooked up text search to front end - full text search
2017-02-12 | Categories CSS classes toggle | Checkout | Add appstrap shop-checkout Page
2017-02-12 | Created Backlog with all outstanding tasks | Checkout | Add appstrap shop-confirmation Page
2017-02-13 | Unit Tests for ar Repo and TextSearch | Checkout | Email With Confirmation - and PDF Invoice
2017-02-13 | Updated Home page with pics & text & video
2017-02-14 | Fixed Header partial view issue - now calls search | Special Offer | Add Bool for Featured Cars, Cars On special
2017-02-14 | fragaria/angular-daterangepicker - not working due to jquery issue | Special Offer | link to special offer/ featuredlist on click Call To Action Links
Daterange picker - values, dates to angular controller
Finish Categories Sidebar and css class issue?
Owl Carousel data-img-zoom not working
Return IHttpActionResult from apiControllers - Ok, Bad Result etc.
Unit Tests - Nunit
Jasmine Tests JS
AutoComplete on text boxes???
Check Thumbnail pics for cars - and change ones not adequate
Add Car List as Grid View
|  | Search | Add Search Bar - 3 x Drop Down Lists - filtered by each selection, make, model, year
Trending Now
Cost Of Rental and calculate based on special offers etc - Update Cost to rent per week
|  | Validation | Validation logic and add modelstate errors etc.
Fade in Divs as scroll down.
|  | Pagination | Change page size, number results, e.g. 15, 20 etc.