## Sheet1
Date | Action | Feature | Backlog | Priority
2017-02-07 | Refactored carService to return promise (via SO question) | Favourites | Add,remove - When users adds it changes fa icon & link text |  | Add second footer with no links - updated info
2017-02-07 | Render pagination links via ng-repeat
2017-02-07 | Set active class of current page when clicked on pagination links. | Login | User can log in from modal |  | Add token to http requests - $http interceptor
2017-02-08 | Moved Categories partial view to angular directive |  |  |  | Drop cookie using ngcookies - $cookieStore
2017-02-08 | Investigate Pagination bug & fix | Homepage | Finish update - complete text, fa icons etc
2017-02-08 | Make start on Details page - pass in Id value | Homepage | Add Google chart to Homepage |  | Limit favourites drop down to show first 5
2017-02-08 | Answer 2 x Stack Overflow Questions
2017-02-08 | Read chapter of Web API 2 book | Reviews | Reviews - and Ratings - Stars fa icons |  | Add Exception handling - add to db
2017-02-09 | Get all Car Info Data (Console app - wikiApi)
2017-02-09 | Added car spec table directive to car details page | Checkout | Make checkout & confirmation pages dynamic |  | Trending Now
2017-02-09 | Read chapter of Design Patterns Book | Checkout | Email With Confirmation - and PDF Invoice - confirmation GUID
2017-02-10 | Added Car Info to DB - added car info service and output to details page | Checkout | Cost Of Rental and calculate based on special offers etc - Update Cost to rent per week |  | Check Thumbnail pics for cars - and change ones not adequate
2017-02-10 | Add images from API call to carousel on Details page |  |  |  | Add missing CarInfo entries
2017-02-11 | Added search algorithm | Special Offer | Add Bool for Featured Cars, Cars On special
2017-02-11 | Investigate Partial view, directive issue - Header | Special Offer | link to special offer/ featuredlist on click Call To Action Links |  | Add Car List as Grid View
2017-02-12 | Hooked up text search to front end - full text search
2017-02-12 | Categories CSS classes toggle |  | Daterange picker - values, dates to angular controller
2017-02-12 | Created Backlog with all outstanding tasks |  | Finish Categories Sidebar |  | 1) ORDERS - Add rental orders to the Db
2017-02-13 | Unit Tests for ar Repo and TextSearch |  | Owl Carousel data-img-zoom not working |  | CarInfo - add for each individual car in list
2017-02-13 | Updated Home page with pics & text & video |  | Footer links
2017-02-14 | Fixed Header partial view issue - now calls search |  |  |  | Create 'My account page' - switch on/off Recommended cars
2017-02-14 | fragaria/angular-daterangepicker - not working due to jquery issue |  | Return IHttpActionResult from apiControllers - Ok, Bad Result etc. |  | Log out - implement
2017-02-15 | Added more unit tests for text search |  | Unit Tests - Nunit
2017-02-16 | Fade in - scroll directive opacity - added |  | Jasmine Tests JS |  | Remove email adress from URLS - cookies
2017-02-16 | Added and updated search Pagination |  | AutoComplete on text boxes???
2017-02-16 | Added Recommended Rentals to Details page - static
2017-02-16 | Add appstrap shop-checkout & confirmation pages static | Validation | Validation logic and add modelstate errors etc.
2017-02-16 | Added new date picker - displays start and end dates
2017-02-17 | Pagination page links - SO question - (created Plunker) | Pagination | Go direct to certain page - eg pg 17
2017-02-17 | Added wishlistController and can get carId's from link click - Details & List
2017-02-18 | Added Log In and Register pages - static | Error Logging | Log errors with Nlog?
2017-02-19 | Register working - user added to AspNetUser table
2017-02-21 | Checkout populated from View Model | Admin Area | Update cars etc.
2017-02-21 | Checkout & Confirmation Pages Working
2017-02-22 | Change page size, number results, e.g. 15, 20 etc. | Email | Send email on registration
2017-02-22 | 3 x Advanced Search DDLS working | Email | Send email on mailing list sign up
2017-02-23 | Moved calendar and drop downs - Details layout
2017-02-23 | Added login service and working - can get token | Recommended | Recommended cars more tailored to users favourite cars