## Sheet1
Date | Action | Feature | Backlog | Priority
2017-02-07 | Refactored carService to return promise (via SO question) | Wishlist | Add Wishlist Table - AspNetUser Id and Car ID
2017-02-07 | Render pagination links via ng-repeat | WishList | Ad to Wishlist - adds record to Db
2017-02-07 | Set active class of current page when clicked on pagination links. | Wishlist | Add Heart & Heart-o - When users adds it chage fa icon
2017-02-08 | Moved Categories partial view to angular directive | Wishlist | Hook up link to show Wishlist and display
2017-02-08 | Investigate Pagination bug & fix | Wishlist | Remove from WishList - remove from Db
2017-02-08 | Make start on Details page - pass in Id value
2017-02-08 | Answer 2 x Stack Overflow Questions | Login | User can log in from modal
2017-02-08 | Read chapter of Web API 2 book
2017-02-09 | Get all Car Info Data (Console app - wikiApi) | Homepage | Finishs update - complete text, fa icons etc
2017-02-09 | Added car spec table directive to car details page | Homepage | Add Google chart to Homepage
2017-02-09 | Read chapter of Design Patterns Book
2017-02-10 | Added Car Info to DB - added car info service and output to details page | Recommended | Recommended & similar cars (dynamic from api controller) Details Page
2017-02-10 | Add images from API call to carousel on Details page
2017-02-11 | Added search algorithm | Reviews | Reviews - and Ratings - Stars fa icons
2017-02-11 | Investigate Partial view, directive issue - Header
2017-02-12 | Hooked up text search to front end - full text search | Checkout | Make checkout & confirmation pages dynamic
2017-02-12 | Categories CSS classes toggle | Checkout | Email With Confirmation - and PDF Invoice
2017-02-12 | Created Backlog with all outstanding tasks
2017-02-13 | Unit Tests for ar Repo and TextSearch | Special Offer | Add Bool for Featured Cars, Cars On special
2017-02-13 | Updated Home page with pics & text & video | Special Offer | link to special offer/ featuredlist on click Call To Action Links
2017-02-14 | Fixed Header partial view issue - now calls search
2017-02-14 | fragaria/angular-daterangepicker - not working due to jquery issue |  | Daterange picker - values, dates to angular controller
2017-02-15 | Added more unit tests for text search |  | Finish Categories Sidebar and css class issue?
2017-02-16 | Fade in - scroll directive opacity - added |  | Owl Carousel data-img-zoom not working
2017-02-16 | Added and updated search Pagination
2017-02-16 | Added Recommended Rentals to Details page - static |  | Return IHttpActionResult from apiControllers - Ok, Bad Result etc.
2017-02-16 | Add appstrap shop-checkout & confirmation pages static |  | Unit Tests - Nunit
2017-02-16 | Added new date picker - displays start and end dates |  | Jasmine Tests JS
2017-02-17 | Pagination page links - SO question - (created Plunker) |  | AutoComplete on text boxes???
2017-02-17 | Added wishlistController and can get carId's from link click - Details & List
2017-02-18 | Added Log In and Register pages - static |  | Check Thumbnail pics for cars - and change ones not adequate
2017-02-19 | Register working - user added to AspNetUser table
2017-02-21 | Checkout populated from View Model |  | Add Car List as Grid View
|  | Search | Add Search Bar - 3 x Drop Down Lists - filtered by each selection, make, model, year
Trending Now
Cost Of Rental and calculate based on special offers etc - Update Cost to rent per week
|  | Validation | Validation logic and add modelstate errors etc.
|  | Pagination | Change page size, number results, e.g. 15, 20 etc.
|  | Pagination | Go direct to certain page - eg pg 17
|  | Logging | Log errors with Nlog?
|  | Admin Area | Update cars etc.